## Projects
Project ID (TP) | PRJ-100
Project name | Falcon Solar PV
Location | Steppe Site 3
GEO | Region A
Country | Region A
Technology | Wind
Capacity | 339 MW
Contract Price | USD 217 Million
Contract Type | IPP / EPC LSTK
Offtaker | Green Fuels Offtake Ltd.
Contractor | Meridian Builders
OEM | SunCell, InvertaTech
O&M | In-house O&M
Contractual Key Dates | [5 empty] | 🟢
Key Milestones | PPA | Capacity | EPC Contract | Forecast |  | Delays
|  |  |  | EPC | PC
LNTP |  |  | 2023-10-06 | 2023-10-06 | 2023-10-06 | 3
NTP |  |  | 2024-07-11 | 2024-07-11 | 2024-07-11 | -1
FC |  |  |  |  | 2025-03-18 | 0
ECD
ECOD1 |  | 110 MW | 2025-12-10 | 2025-12-10 | 2025-12-10 | 2
ECOD2 |  | 110 MW | 2026-01-25 | 2026-01-25 | 2026-03-26 | 0
ECOD3 |  |  | 2026-02-24 | 2026-02-24 | 2026-03-26 | 3
PCOD | 2027-07-05 | 119.3 MW | 2026-03-13 | 2026-03-13 | 2026-04-12 | 0
[7 empty] | No | Key Milestone (Monthly) | Baseline Date | Forecast Date | Actual Date

## Key Concerns Mitigations,QA QC
Key Concerns and Mitigations
Key Concerns | Mitigations | Severity | Impact | Severity: | Low | Medium | High
Subcontractor mobilisation behind plan for civil works. | Weekly coordination meetings held with the grid operator; phased approvals proposed. | High | Schedule
Design change requested by the offtaker for the substation layout. | Claim is being reviewed against contract entitlements. | Low | Finance
Late delivery of main power transformers from the OEM factory. | Claim is being reviewed against contract entitlements. | Low | Schedule
Shortage of skilled electricians during peak installation period. | Expedited shipping agreed with the OEM; factory inspections moved forward. | High | Schedule
Grid connection studies pending approval from the transmission operator; risk to energisation date. | Change order under evaluation; interim design frozen for non-affected areas. | Low | Contractual
QA/QC | Values
FAT (Actual / Total) | 81/142
NCR (Open / Total) | 34/57
Critical NCRs | 0
SOR (Site Observation Report) | 0
TOP (Actual / Total) | N/A

## Project Progress
Project Progress |  |  |  |  | Payment Milestones Progress |  |  |  | Key Achievements
Category | Weight | Early | Late | Actual | Category | Weight | Plan | Actual
Engineering | 10% | 100% | 100% | 99.83% | Onshore | 26.76% | 32.26% | 20.97% | Foundation works for all turbines completed.
Procurement | 35% | 100% | 95.35% | 98.26% | Offshore | 73.24% | 73.64% | 58.98% | First block of PV modules installed ahead of plan.
Construction | 45% | 75.45% | 53.32% | 44.48% | Overall | 100% | 95.05% | 72.36%
Commissioning | 10% | 39.94% | 3.319% | 9.303%
OVERALL | 100% | 83.44% | 69.43% | 67.17%

## Contractor Claims
Contractor Claims
Total Cost Claim | Total Extension of Time Claim | Remarks
-200000 |  | Under review
-164175 |  | Under review
3500000 |  | Negotiation ongoing
273169 |  | Under review
47254 |  | Partially accepted
-63141 |  | Under review
| 6 months | Negotiation ongoing

## Critical Path Analysis
Critical Path Analysis | Float(d)
Grid Studies > Substation Energisation > Backfeed > COD | 7 days

## Project Key Milestones
Project Key Milestones
Sr. No. | Key Milestone (Monthly) | Baseline Date | Forecast Date | Actual Date
1 | EPC contract signed | 2023-10-06 |  | 2023-10-06
2 | Limited notice to proceed | 2023-11-24 |  | 2023-11-24
3 | Full notice to proceed | 2023-12-23 |  | 2023-12-23
4 | Financial close | 2024-08-06 |  | 2024-07-11
5 | Detailed design 50% complete | 2024-07-11 |  | 2024-08-06
6 | Main equipment orders placed | 2024-09-02 |  | 2024-08-20
7 | Site mobilisation | 2024-09-03 |  | 2024-09-11
8 | Piling works start | 2024-08-15 |  | 2024-09-16
9 | Foundations complete | 2024-11-24 |  | 2024-12-24
10 | Main equipment delivered | 2024-12-19 |  | 2024-12-25
11 | Substation energisation | 2024-12-28 |  | 2025-02-08
12 | Block 1 mechanical completion | 2025-02-12 |  | 2025-03-19
13 | Block 2 mechanical completion | 2025-11-12 | 2025-11-12
14 | Backfeed power available | 2025-11-17 | 2025-11-17
15 | First power / synchronisation | 2025-05-15 | 2025-11-26
16 | Block 1 commissioning | 2025-12-28 | 2025-12-28
17 | Block 2 commissioning | 2025-07-12 | 2025-11-08
18 | Reliability run | 2026-01-02 | 2026-01-02
19 | Performance test | 2025-12-01 | 2025-12-01
20 | Partial commercial operation | 2025-12-10 | 2025-12-10
21 | Commercial operation date | 2026-01-02 | 2026-01-02
22 | Punch-list closure | 2026-01-16 | 2026-01-16
23 | Final acceptance | 2026-01-25 | 2026-01-25
24 | EPC contract signed | 2026-02-05 | 2026-02-05
25 | Limited notice to proceed | 2026-02-15 | 2026-02-15
26 | Full notice to proceed | 2026-02-24 | 2026-02-24
27 | Financial close | 2026-03-12 | 2026-03-12
28 | Detailed design 50% complete | 2026-03-13 | 2026-03-13
29 | Main equipment orders placed | 2026-03-13 | 2026-03-13

## S-Curve
Date | No. | Project Baseline Early T0 |  | Project Baseline Late T0 |  | Actual |  | Forecast
|  | Monthly Progress (%) | Ac, Progress (%) | Monthly Progress (%) | Ac, Progress (%) | Monthly Progress (%) | Ac, Progress (%) | Monthly Progress (%) | Ac, Progress (%)
2023-10-29 | 1 | 5.468% | 5.468% | 4.918% | 4.918% | 5.468% | 5.468%
2023-11-26 | 2 | 2.893% | 8.361% | 2.944% | 7.863% | 2.893% | 8.361%
2023-12-24 | 3 | 0.218% | 8.579% | 0.2209% | 8.083% | 0.218% | 8.579%
2024-01-28 | 4 | 1.913% | 10.49% | 1.935% | 10.02% | 1.913% | 10.49%
2024-02-25 | 5 | 3.375% | 13.87% | 3.404% | 13.42% | 3.367% | 13.86%
2024-03-24 | 6 | 1.711% | 15.58% | 1.722% | 15.14% | 1.711% | 15.57%
2024-04-28 | 7 | 5.01% | 20.59% | 5.036% | 20.18% | 5.01% | 20.58%
2024-05-26 | 8 | 1.937% | 22.52% | 1.945% | 22.12% | 1.937% | 22.52%
2024-06-23 | 9 | 0.9557% | 23.48% | 0.9593% | 23.08% | 0.9557% | 23.47%
2024-07-28 | 10 | 1.432% | 24.91% | 1.437% | 24.52% | 1.979% | 25.45%
2024-08-25 | 11 | 3.179% | 28.09% | 0.2961% | 24.82% | 2.355% | 27.81%
2024-09-29 | 12 | 5.8% | 33.89% | 1.974% | 26.79% | 4.165% | 31.97%
2024-10-27 | 13 | 3.932% | 37.82% | 1.808% | 28.6% | 2.799% | 34.77%
2024-11-24 | 14 | 4.947% | 42.77% | 2.396% | 31% | 3.581% | 38.35%
2024-12-29 | 15 | 5.737% | 48.51% | 2.628% | 33.62% | 6.321% | 44.67%
2025-01-26 | 16 | 3.109% | 51.62% | 2.631% | 36.25% | 3.439% | 48.11%
2025-02-23 | 17 | 3.78% | 55.39% | 3.263% | 39.52% | 2.208% | 50.32%
2025-03-30 | 18 | 5.145% | 60.54% | 4.733% | 44.25% | 3.12% | 53.44%
2025-04-27 | 19 | 4.79% | 65.33% | 4.582% | 48.83% | 2.801% | 56.24%
2025-06-01 | 20 | 5.115% | 70.44% | 6.478% | 55.31% | 2.708% | 58.95%
2025-06-29 | 21 | 5.213% | 75.66% | 4.675% | 59.99% | 1.669% | 60.62%
2025-07-27 | 22 | 3.406% | 79.06% | 4.556% | 64.54% | 2.576% | 63.19%
2025-08-24 | 23 | 4.371% | 83.43% | 4.89% | 69.43% | 3.972% | 67.16%
2025-09-28 | 24 | 5.075% | 88.51% | 5.395% | 74.83% |  |  | 0% | 79.64%
2025-10-26 | 25 | 3.534% | 92.04% | 4.519% | 79.35% |  |  | 6.57% | 86.21%
2025-11-23 | 26 | 3.047% | 95.09% | 5.642% | 84.99% |  |  | 5.642% | 91.85%
2025-12-28 | 27 | 3.277% | 98.37% | 6.033% | 91.02% |  |  | 4.622% | 96.47%
2026-01-25 | 28 | 1.241% | 99.61% | 6.251% | 97.27% |  |  | 2.655% | 99.13%
2026-03-01 | 29 | 0.3926% | 100% | 2.729% | 100% |  |  | 0.8748% | 100%
2026-03-08 | 30 | 0% | 100% | 0% | 100% |  |  | 5.447e-05% | 100%

## Payment Milestones S-curve
Date | Plan Cum % | Actual Cum % | Forecast Cum %
2024-04-30 | 20.59% | 0%
2024-05-30 | 22.89% | 0%
2024-06-29 | 28.63% | 0%
2024-07-29 | 33.82% | 5.478%
2024-08-28 | 41.08% | 30.23%
2024-09-27 | 48.9% | 33.63%
2024-10-27 | 56.54% | 35.93%
2024-11-26 | 61.57% | 36.43%
2024-12-26 | 65.96% | 36.94%
2025-01-25 | 71.11% | 47.52%
2025-02-24 | 75.96% | 52.74%
2025-03-26 | 80.32% | 52.74%
2025-04-25 | 83.28% | 69.05%
2025-05-25 | 87.37% | 69.05%
2025-06-24 | 90.38% | 70.63%
2025-07-24 | 93.39% | 70.63%
2025-08-23 | 95.05% | 72.38%
2025-09-22 | 95.88%
2025-10-22 | 96.71%
2025-11-21 | 97.53%
2025-12-21 | 100%

## Cost Contingency
Cost/Contingency
Project Costs (MUSD) |  |  | Contingency (MUSD)
Base Case | Forecast | Cost Overun | Base Case | Utilized | Forecast | Potential Savings
551.9 | 582.6 | 30.7 | 4.3 |  | 4.2

## Source Of Founding
Head | Value | Sponsor Share | Partners Share
Contingency | 4.2
Standby Equity | 0
Standby Debt | 0
Additional Loans | 0
Additional EBL | 0
Additional EGR | 34.6
Withheld EPC Milestone Payment | 37.4
LDs | 38.5
WCF | 0
Shareholder injection | 0
Unresolved | 0