## Projects
Project ID (TP) | PRJ-103
Project name | Horizon Solar PV
Location | Coastal Zone B
GEO | Region B
Country | Region B
Technology | PV
Capacity | 1441 MW
Contract Price | 1,260 Mn USD
Contract Type | Split EPC
Offtaker | Utility Holding Co.
Contractor | Northstar Engineering JV
OEM | PanelWorks, PowerStack
O&M | In-house O&M
Contractual Key Dates | [5 empty] | 🟢
Key Milestones | PPA | Capacity | EPC Contract | Forecast |  | Delays
|  |  |  | EPC | PC
LNTP | 2023-08-19 |  | 2023-08-19 | 2023-09-23 | 2023-09-23 | 2
NTP | 2023-11-18 |  | 2023-11-19 | 2023-11-19 | 2023-11-19 | 0
FC | 2023-12-07 |  |  | 2024-03-12 | 2024-03-12 | 0
ECD | 2025-02-18 |  | 2025-02-18 | 2025-08-18 | 2025-08-18 | 3 | being delayed further
ICOD1 | 2025-06-18 | 721 MW | 2025-06-18 | 2025-11-02 | 2025-11-02 | -2
ICOD2 | 2025-10-18 | 1441MW | 2025-10-18 | 2025-12-08 | 2025-12-08 | 1
PCOD | 2026-08-18 | 1441MW | 2026-08-18 | 2026-08-18 | 2026-08-18 | -2
[8 empty] | No | Key Milestone (Monthly) | Baseline Date | Forecast Date | Actual Date

## Key Concerns Mitigations,QA QC
Key Concerns and Mitigations
Key Concerns | Mitigations | Severity | Impact | Severity: | Low | Medium | High
Contractor has submitted an extension-of-time notice under review. | Night shifts introduced for critical activities. | Medium | HSE
Extreme summer temperatures limiting working hours on site. | Change order under evaluation; interim design frozen for non-affected areas. | Medium | Schedule
Subcontractor mobilisation behind plan for civil works. |  | High | Finance
Grid connection studies pending approval from the transmission operator; risk to energisation date. |  | High | QA/QC
Extreme summer temperatures limiting working hours on site. |  | Low | Finance
Design change requested by the offtaker for the substation layout. | Night shifts introduced for critical activities. | Low | Contractual
QA/QC | Values
FAT (Actual / Total) | 187/464
NCR (Open / Total) | 23/26
Critical NCRs | 3
SOR (Site Observation Report) | 2
TOP (Actual / Total) | 33/40

## Project Progress
Project Progress |  |  |  |  | Payment Milestones Progress |  |  |  | Key Achievements
Category | Weight | Early | Late | Actual | Category | Weight | Plan | Actual
Preliminary & Permitting | 1% | 100% | 100% | 97.68% |  |  |  |  | Foundation works for all turbines completed.
Engineering | 10% | 100% | 100% | 99.1% | Onshore | 87.19% | 94.14% | 92.03% | Inverter station pre-commissioning started.
Procurement | 35% | 100% | 100% | 100% | Offshore | 12.81% | 100% | 100% | Seawater intake structure completed.
Construction | 44% | 99.99% | 98.13% | 99.73% | Overall | 100% | 94.88% | 93.05% | Tracker installation completed for Phase 1.
Commissioning | 10% | 81.48% | 66.84% | 55.06% |  |  |  |  | Inverter station pre-commissioning started.
OVERALL | 100% | 98.12% | 95.77% | 95.09%

## Contractor Claims
Contractor Claims
Total Cost Claim | Total Extension of Time Claim | Remarks
12.59 | 3 months | Under review

## Critical Path Analysis
Critical Path Analysis | Float(d)
Grid Studies > Substation Energisation > Backfeed > COD | 0 days
Grid Studies > Substation Energisation > Backfeed > COD | 0 days

## Project Key Milestones
Project Key Milestones
Sr. No. | Key Milestone (Monthly) | Baseline Date | Forecast Date | Actual Date
1 | EPC contract signed | 2024-05-09 |  | 2024-06-25
2 | Limited notice to proceed | 2024-05-25 |  | 2024-08-05
3 | Full notice to proceed | 2024-06-30 |  | 2024-06-04
4 | Financial close | 2024-08-13 |  | 2024-08-10
5 | Detailed design 50% complete | 2024-09-01 |  | 2024-09-12
6 | Main equipment orders placed | 2024-10-10 |  | 2024-11-09
7 | Site mobilisation | 2024-10-31 |  | 2024-12-17
8 | Piling works start | 2024-10-18 |  | 2025-02-16
9 | Foundations complete | 2024-09-28 |  | 2024-11-20
10 | Main equipment delivered | 2024-12-12 |  | 2025-01-05
11 | Substation energisation | 2024-12-24 |  | 2024-09-24
12 | Block 1 mechanical completion | 2024-12-19 |  | 2025-03-20
13 | Block 2 mechanical completion | 2025-02-15 |  | 2025-02-02
14 | Backfeed power available | 2025-03-14 |  | 2025-04-10
15 | First power / synchronisation | 2025-02-18 | 2025-08-18 |  | Further delayed.
16 | Block 1 commissioning | 2025-03-16 | 2025-09-13
17 | Block 2 commissioning | 2025-03-22 |  | 2025-06-07 | Partial Hot Commissioning has started from 17th February 2025; while full sustained hot commissioning shall start after Energization.
18 | Reliability run | 2025-04-08 | 2025-09-20
19 | Performance test | 2025-06-03 | 2025-10-18
20 | Partial commercial operation | 2025-06-18 | 2025-11-02
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36

## S-Curve
Date | No. | Project Baseline Early T0 |  | Project Baseline Late T0 |  | Actual |  | Forecast
|  | Monthly Progress (%) | Ac, Progress (%) | Monthly Progress (%) | Ac, Progress (%) | Monthly Progress (%) | Ac, Progress (%) | Monthly Progress (%) | Ac, Progress (%)
2023-09-10 | -2 | 0% | 0% | 0% | 0% | 0% | 0%
2023-10-11 | -1 | 0.2313% | 0.2313% | 0% | 0% | 0.5429% | 0.5429%
2023-11-10 | 3 | 0.9081% | 1.139% | 0.03716% | 0.03716% | 1.578% | 2.121%
2023-12-11 | 4 | 0.8649% | 2.004% | 0.3429% | 0.38% | 1.116% | 3.237%
2024-01-11 | 5 | 1.608% | 3.613% | 0.5109% | 0.8909% | 0.9171% | 4.154%
2024-02-10 | 6 | 1.56% | 5.173% | 0.7927% | 1.684% | 1.549% | 5.703%
2024-03-12 | 7 | 1.984% | 7.156% | 1.537% | 3.221% | 1.83% | 7.533%
2024-04-11 | 8 | 2.259% | 9.416% | 1.472% | 4.693% | 2.784% | 10.32%
2024-05-12 | 9 | 3.288% | 12.7% | 1.797% | 6.49% | 3.629% | 13.95%
2024-06-12 | 10 | 4.364% | 17.07% | 2.075% | 8.564% | 5.185% | 19.13%
2024-07-11 | 11 | 5.476% | 22.54% | 2.831% | 11.4% | 7.555% | 26.69%
2024-08-11 | 12 | 6.047% | 28.59% | 3.648% | 15.04% | 4.261% | 30.95%
2024-09-10 | 13 | 7.933% | 36.52% | 5.255% | 20.3% | 7.36% | 38.31%
2024-10-11 | 14 | 8.048% | 44.57% | 5.855% | 26.15% | 7.729% | 46.04% |  |  | 0.0053029 | 0.01211 | 0.011198 | 0.006284 | 0.0013297 | 0.0012408 | 0.001551 | 0.00071506 | 0.00058516 | 0.00045243 | 0.00036088 | 0.00021966 | 5.766e-05
2024-11-10 | 15 | 9.284% | 53.86% | 7.864% | 34.02% | 9.9% | 55.94% |  |  | 0.96392 | 0.97603 | 0.98723 | 0.99351 | 0.99484 | 0.99608 | 0.99764 | 0.99835 | 0.99894 | 0.99939 | 0.99975 | 0.99997 | 1
2024-12-11 | 16 | 8.885% | 62.74% | 8.264% | 42.28% | 7.856% | 63.79%
2025-01-11 | 17 | 8.2% | 70.94% | 8.961% | 51.24% | 5.952% | 69.74%
2025-02-10 | 18 | 6.554% | 77.49% | 8.739% | 59.98% | 6.552% | 76.3%
2025-03-13 | 19 | 6.14% | 83.63% | 8.868% | 68.85% | 6.172% | 82.47%
2025-04-12 | 20 | 4.692% | 88.32% | 8.666% | 77.52% | 4.411% | 86.88%
2025-05-13 | 21 | 4.224% | 92.55% | 6.558% | 84.07% | 3.708% | 90.59%
2025-06-13 | 22 | 2.88% | 95.43% | 5.778% | 89.85% | 2.038% | 92.63%
2025-07-11 | 23 | 1.652% | 97.08% | 3.058% | 92.91% | 1.723% | 94.35%
2025-08-11 | 24 | 1.037% | 98.12% | 2.855% | 95.77% | 0.7457% | 95.09%
2025-09-10 | 25 | 0.7322% | 98.85% | 1.688% | 97.46% |  |  | 0% | 95.72%
2025-10-11 | 26 | 0.3528% | 99.2% | 1.456% | 98.91% |  |  | 1.433% | 97.15%
2025-11-10 | 27 | 0.1718% | 99.37% | 0.2251% | 99.14% |  |  | 1.328% | 98.48%
2025-12-11 | 28 | 0.1025% | 99.48% | 0.1025% | 99.24% |  |  | 0.7465% | 99.23%
2026-01-11 | 29 | 0.1025% | 99.58% | 0.1025% | 99.34% |  |  | 0.1581% | 99.39%
2026-02-10 | 30 | 0.1026% | 99.68% | 0.1025% | 99.44% |  |  | 0.1475% | 99.53%
2026-03-13 | 31 | 0.1014% | 99.78% | 0.1025% | 99.55% |  |  | 0.1845% | 99.72%
2026-04-12 | 32 | 0.04142% | 99.83% | 0.1025% | 99.65% |  |  | 0.08507% | 99.8%
2026-05-13 | 33 | 0.04783% | 99.87% | 0.109% | 99.76% |  |  | 0.06963% | 99.87%
2026-06-13 | 34 | 0.05384% | 99.93% | 0.112% | 99.87% |  |  | 0.05384% | 99.93%
2026-07-11 | 35 | 0.03483% | 99.96% | 0.07243% | 99.94% |  |  | 0.04295% | 99.97%
2026-08-11 | 36 | 0.03159% | 99.99% | 0.051% | 99.99% |  |  | 0.02614% | 100%
2026-09-10 | 37 | 0.006722% | 100% | 0.006798% | 100% |  |  | 0.003684% | 100%
2026-10-11 | 38 | 0% | 100% | 0% | 100%
2026-11-10 | 39 | 0% | 100% | 0% | 100%
2026-12-11 | 40 | 0% | 100% | 0% | 100%
2027-01-11 | 41 | 0% | 100% | 0% | 100%
2027-02-10 | 42 | 0% | 100% | 0% | 100%
2027-03-13 | 43 | 0% | 100% | 0% | 100%

## Payment Milestones S-curve
Date | Plan Cum % | Actual Cum % | Forecast Cum %
2025-09-18 | 0% | 0%
2023-10-18 | 0.8112% | 0.5097%
2023-11-18 | 1.027% | 0.5097%
2023-12-18 | 2.158% | 2.138%
2023-12-19 | 2.158% | 2.138%
2024-01-18 | 6.303% | 6.305%
2024-02-18 | 8.839% | 8.836%
2024-03-19 | 10.5% | 10.51%
2024-04-19 | 12.24% | 12.28%
2024-05-19 | 16.42% | 12.28%
2024-06-18 | 21.12% | 20.2%
2024-07-18 | 26.6% | 26.2%
2024-08-18 | 33.19% | 30.28%
2024-09-17 | 39.99% | 37.17%
2024-10-18 | 45.97% | 41.8%
2024-11-18 | 52.08% | 48.49%
2024-12-19 | 58.31% | 56.91%
2025-01-18 | 65.71% | 57.54%
2025-02-18 | 73.25% | 68.78%
2025-03-20 | 79.81% | 75.33%
2025-04-20 | 86.46% | 82.88%
2025-05-21 | 92.06% | 87.73%
2025-06-18 | 94.32% | 89.86%
2025-07-19 | 94.6% | 92.17%
2025-08-18 | 94.89% | 93.04%
2025-09-17 | 95.17%
2025-10-18 | 95.45%
2025-11-18 | 96.36%
2025-12-19 | 97.27%
2026-01-18 | 97.72%
2026-02-18 | 98.18%
2026-03-20 | 98.63%
2026-04-20 | 99.09%
2026-05-21 | 99.32%
2026-06-18 | 99.54%
2026-07-19 | 99.77%
2026-08-18 | 100%
2026-09-18 | 100%
2026-10-18 | 100%

## Cost Contingency
Cost/Contingency
Project Costs (MUSD) |  |  | Contingency (MUSD)
Base Case | Forecast | Cost Overun | Base Case | Utilized | Forecast | Potential Savings
1775.9 | 1655 | -120.9 | 13.9 |  | 12.5

## Source Of Founding
Head | Value | Sponsor Share | Partners Share
Contingency | 0
Standby Equity | 0
Standby Debt | 0
Additional Loans | 0
Additional EBL | 0
Additional EGR | 0
Withheld EPC Milestone Payment | 0
LDs | 0
WCF | 0
Shareholder injection | 6.8
Unresolved | 0