## Projects
Project ID (TP) | PRJ-116
Project name | Topaz CSP Plant
Location | Canal Industrial Zone
GEO | Region C
Country | Region C
Technology | CSP
Capacity | 111 MW
Contract Price | USD 996 Million
Contract Type | EPC LSTK
Offtaker | Green Fuels Offtake Ltd.
Contractor | Atlas EPC / Vertex JV
OEM | PanelWorks, PowerStack
O&M | In-house O&M
Contractual Key Dates | [5 empty] | 🟢
Key Milestones | PPA | Capacity | EPC Contract | Forecast |  | Delays
|  |  |  | EPC | PC
LNTP | 2021-03-20 |  | 2021-03-20 | 2021-03-20 | 2021-03-20 | 3
NTP | 2021-06-17 |  | 2021-06-17 | 2021-06-17 | 2021-06-17 | -1
COD | 2024-03-22 | 111 MW | 2025-07-10 | 2025-07-10 | 2025-07-10 | -1
IAD |  | 111 MW |  | 2025-08-23 | 2025-08-23 | 0
[7 empty] | No | Key Milestone (Monthly) | Baseline Date | Forecast Date | Actual Date

## Key Concerns Mitigations,QA QC
Key Concerns and Mitigations
Key Concerns | Mitigations | Severity | Impact | Severity: | Low | Medium | High
Shortage of skilled electricians during peak installation period. | Expedited shipping agreed with the OEM; factory inspections moved forward. | Low | Schedule
Customs clearance delays for imported modules. | Expedited shipping agreed with the OEM; factory inspections moved forward. | High | Schedule
Shortage of skilled electricians during peak installation period. | Recovery schedule requested from the contractor and tracked weekly. | Low | Cost
Shortage of skilled electricians during peak installation period. | Recovery schedule requested from the contractor and tracked weekly. | Medium | QA/QC
Late delivery of main power transformers from the OEM factory. | Recovery schedule requested from the contractor and tracked weekly. | Low | QA/QC
Contractor has submitted an extension-of-time notice under review. | Change order under evaluation; interim design frozen for non-affected areas. | High | HSE
Grid connection studies pending approval from the transmission operator; risk to energisation date. | Night shifts introduced for critical activities. | High | Cost
QA/QC | Values
FAT (Actual / Total) | 60/117
NCR (Open / Total) | 109/193
Critical NCRs | 0
SOR (Site Observation Report) | 3
TOP (Actual / Total) | 181/340

## Project Progress
Project Progress |  |  |  |  | Payment Milestones Progress |  |  |  | Key Achievements
Category | Weight | Early | Late | Actual | Category | Weight | Plan | Actual
Engineering | 10% | 100% | 100% | 100% | Onshore | 34.7% | 41.11% | 38.81% | Foundation works for all turbines completed.
Procurement | 40% | 100% | 100% | 99.87% | Offshore | 65.3% | 69.91% | 68.56% | Cold commissioning of the first unit completed.
Construction | 40% | 100% | 100% | 99.74% | Overall | 100% | 100% | 96.8% | 1,000,000 safe man-hours achieved without LTI.
Commissioning | 10% | 100% | 100% | 95.66% |  |  |  |  | Seawater intake structure completed.
OVERALL | 100% | 100% | 100% | 99.41% |  |  |  |  | Main substation energised successfully.

## Contractor Claims
Contractor Claims
Total Cost Claim | Total Extension of Time Claim | Remarks
| 8 months | Negotiation ongoing
| 9 months | Rejected

## Critical Path Analysis
Critical Path Analysis | Float(d)
Grid Studies > Substation Energisation > Backfeed > COD | 0 days

## Project Key Milestones
Project Key Milestones
Sr. No. | Key Milestone (Monthly) | Baseline Date | Forecast Date | Actual Date
1 | EPC contract signed | 2023-09-16 | 2024-05-15 | 2024-05-17
2 | Limited notice to proceed | 2024-01-10 | 2024-04-20 | 2024-04-23
3 | Full notice to proceed | 2024-01-05 | 2024-06-01 | 2024-04-25
4 | Financial close | 2024-01-11 | 2024-08-30 | 2024-09-05
5 | Detailed design 50% complete | 2023-08-12 | 2024-06-11 | 2024-06-01
6 | Main equipment orders placed | 2023-10-05 | 2024-06-16 | 2024-06-16
7 | Site mobilisation | 2024-01-11 | 2024-07-07 | 2024-05-09
8 | Piling works start | 2023-09-19 | 2024-07-13 | 2024-07-09
9 | Foundations complete | 2023-08-17 | 2024-07-16 | 2024-07-16
10 | Main equipment delivered | 2023-10-22 | 2024-07-17 | 2024-07-17
11 | Substation energisation | 2024-03-07 | 2024-08-25 | 2024-08-11
12 | Block 1 mechanical completion | 2024-01-19 | 2024-10-03 | 2024-10-19
13 | Block 2 mechanical completion | 2023-10-15 | 2024-08-01 | 2024-08-16
14 | Backfeed power available | 2023-11-09 | 2024-08-16 | 2024-08-16
15 | First power / synchronisation | 2024-04-14 | 2024-10-05 | 2024-10-26
16 | Block 1 commissioning | 2023-10-26 | 2024-08-20 | 2024-09-16
17 | Block 2 commissioning | 2023-11-27 | 2024-09-16 | 2024-09-16
18 | Reliability run | 2023-05-07 | 2025-06-01 | 2025-06-20
19 | Performance test | 2024-10-06 | 2024-10-26 | 2024-10-31
20 | Partial commercial operation | 2024-10-17 | 2025-07-10
21 | Commercial operation date | 2024-06-10 | 2025-07-09
22 | Punch-list closure | 2024-03-24 | 2025-07-13
23 | Final acceptance | 2024-06-13 | 2025-08-25

## S-Curve
Date | No. | Project Baseline Early T0 |  | Project Baseline Late T0 |  | Actual |  | Forecast
|  | Monthly Progress (%) | Ac, Progress (%) | Monthly Progress (%) | Ac, Progress (%) | Monthly Progress (%) | Ac, Progress (%) | Monthly Progress (%) | Ac, Progress (%)
2021-04-01 | -1 | 0.5885% | 0.5885% | 0.1287% | 0.1287% | 0.4911% | 0.4911%
2021-05-01 | 1 | 1.146% | 1.734% | 0.3145% | 0.4432% | 1.407% | 1.898%
2021-06-01 | 2 | 3.142% | 4.876% | 0.8533% | 1.297% | 2.318% | 4.217%
2021-07-01 | 3 | 4.11% | 8.986% | 1.487% | 2.783% | 2.282% | 6.499%
2021-08-01 | 4 | 4.771% | 13.76% | 2.93% | 5.713% | 4.651% | 11.15%
2021-09-01 | 5 | 4.697% | 18.45% | 3.227% | 8.94% | 4.14% | 15.29%
2021-10-01 | 6 | 4.802% | 23.26% | 3.549% | 12.49% | 4.057% | 19.35%
2021-11-01 | 7 | 5.567% | 28.82% | 4.297% | 16.79% | 3.648% | 22.99%
2021-12-01 | 8 | 5.838% | 34.66% | 3.99% | 20.78% | 4.47% | 27.47%
2022-01-01 | 9 | 5.626% | 40.29% | 4.355% | 25.13% | 4.53% | 32%
2022-02-01 | 10 | 4.606% | 44.89% | 3.834% | 28.97% | 4.279% | 36.27%
2022-03-01 | 11 | 5.186% | 50.08% | 4.509% | 33.47% | 2.702% | 38.98%
2022-04-01 | 12 | 4.771% | 54.85% | 4.114% | 37.59% | 3.588% | 42.56%
2022-05-01 | 13 | 4.791% | 59.64% | 4.386% | 41.97% | 3.375% | 45.94%
2022-06-01 | 14 | 4.321% | 63.96% | 4.501% | 46.47% | 2.356% | 48.3%
2022-07-01 | 15 | 4.437% | 68.4% | 3.707% | 50.18% | 3.631% | 51.93%
2022-08-01 | 16 | 3.887% | 72.29% | 4.014% | 54.2% | 2.69% | 54.62%
2022-09-01 | 17 | 3.723% | 76.01% | 4.36% | 58.56% | 0.546% | 55.16%
2022-10-01 | 18 | 4.663% | 80.67% | 4.938% | 63.49% | 2.184% | 57.35%
2022-11-01 | 19 | 4.635% | 85.31% | 5.072% | 68.57% | 3.112% | 60.46%
2022-12-01 | 20 | 4.818% | 90.13% | 5.32% | 73.89% | 3.677% | 64.14%
2023-01-01 | 21 | 3.287% | 93.41% | 5.492% | 79.38% | 2.051% | 66.19%
2023-02-01 | 22 | 2.616% | 96.03% | 5.306% | 84.68% | 3.751% | 69.94%
2023-03-01 | 23 | 1.822% | 97.85% | 4.948% | 89.63% | 0.1888% | 70.13%
2023-04-01 | 24 | 1.097% | 98.95% | 3.186% | 92.82% | 3.916% | 74.04%
2023-05-01 | 25 | 0.4257% | 99.37% | 1.946% | 94.76% | 1.81% | 75.85%
2023-06-01 | 26 | 0.1433% | 99.52% | 1.512% | 96.28% | 3.412% | 79.26%
2023-07-01 | 27 | 0.2243% | 99.74% | 1.389% | 97.66% | 3.619% | 82.88%
2023-08-01 | 28 | 0.09696% | 99.84% | 0.6954% | 98.36% | 2.457% | 85.34%
2023-09-01 | 29 | 0.08102% | 99.92% | 0.5984% | 98.96% | 1.228% | 86.57%
2023-10-01 | 30 | 0.08103% | 100% | 1.041% | 100% | 0.7677% | 87.34%
2023-11-01 | 31 | 0% | 100% | 0% | 100% | 1.085% | 88.42%
2023-12-01 | 32 | 0% | 100% | 0% | 100% | 1.836% | 90.26%
2024-01-01 | 33 | 0% | 100% | 0% | 100% | 1.146% | 91.4%
2024-02-01 | 34 | 0% | 100% | 0% | 100% | 1.237% | 92.64%
2024-03-01 | 35 | 0% | 100% | 0% | 100% | 0.5196% | 93.16%
2024-04-01 | 36 | 0% | 100% | 0% | 100% | 1.029% | 94.19%
2024-05-01 | 37 | 0% | 100% | 0% | 100% | 0.484% | 94.67%
2024-06-01 | 38 | 0% | 100% | 0% | 100% | 1.009% | 95.68%
2024-07-01 | 39 | 0% | 100% | 0% | 100% | 0.7702% | 96.45%
2024-08-01 | 40 | 0% | 100% | 0% | 100% | 0.5156% | 96.97%
2024-09-01 | 41 | 0% | 100% | 0% | 100% | 0.7092% | 97.68%
2024-10-01 | 42 | 0% | 100% | 0% | 100% | 0.1856% | 97.86%
2024-11-01 | 43 | 0% | 100% | 0% | 100% | 0.4552% | 98.32%
2024-12-01 | 44 | 0% | 100% | 0% | 100% | 0.1348% | 98.45%
2025-01-01 | 45 | 0% | 100% | 0% | 100% | 0.6567% | 99.11%
2025-02-01 | 46 | 0% | 100% | 0% | 100% | 0.1935% | 99.3%
2025-03-01 | 47 | 0% | 100% | 0% | 100% | 0.0841% | 99.39%
2025-04-01 | 48 | 0% | 100% | 0% | 100% | 0.02523% | 99.41%
2025-05-01 | 49 | 0% | 100% | 0% | 100% |  |  | 0% | 99.78%
2025-06-01 | 50 | 0% | 100% | 0% | 100% |  |  | 0.1993% | 99.98%
2025-07-01 | 51 | 0% | 100% | 0% | 100% |  |  | 0.01797% | 100%

## Payment Milestones S-curve
Date | Plan Cum % | Actual Cum % | Forecast Cum %
1899-12-31 | 8.718% | 3.163%
1899-12-31 | 9.154% | 8.172%
1899-12-31 | 13.21% | 8.58%
1899-12-31 | 15.94% | 11.1%
1899-12-31 | 19.89% | 13.6%
1899-12-31 | 24.1% | 13.6%
1899-12-31 | 28.67% | 16.1%
1899-12-31 | 32.82% | 16.66%
1899-12-31 | 37.21% | 17.59%
1899-12-31 | 40.44% | 23.65%
1899-12-31 | 43.89% | 28.94%
1899-12-31 | 48.31% | 31.92%
1899-12-31 | 52.12% | 35.09%
1899-12-31 | 56.12% | 38.66%
1899-12-31 | 59.77% | 40.76%
1899-12-31 | 64.81% | 42.61%
1899-12-31 | 68.85% | 44.38%
1899-12-31 | 73.02% | 50.6%
1899-12-31 | 76.62% | 52.64%
1899-12-31 | 80.07% | 60.86%
1899-12-31 | 82.55% | 67.57%
1899-12-31 | 85.04% | 67.57%
1899-12-31 | 87.4% | 71.56%
1899-12-31 | 89.39% | 77.18%
1899-12-31 | 91.25% | 80.33%
1899-12-31 | 93.13% | 82.78%
1899-12-31 | 94.99% | 83.76%
1899-12-31 | 96.85% | 85.9%
1899-12-31 | 98.36% | 88.4%
1899-12-31 | 99.84% | 90.84%
1899-12-31 | 100% | 91.61%
1899-12-31 | 100% | 92.76%
1899-12-31 | 100% | 94.66%
1899-12-31 | 100% | 95.34%
1899-12-31 | 100% | 96.12%
1899-12-31 | 100% | 96.5%
1899-12-31 | 100% | 96.5%
1899-12-31 | 100% | 96.66%
1899-12-31 | 100% | 96.66%
1899-12-31 | 100% | 96.69%
1899-12-31 | 100% | 96.69%
1899-12-31 | 100% | 96.8%
1899-12-31 | 100% | 96.8%
1899-12-31 | 100% | 96.8%
1899-12-31 | 100% | 96.8%
1899-12-31 | 100% | 96.8%
1899-12-31 | 100% | 96.8%
1899-12-31 | 100%
1899-12-31 | 100%
1899-12-31 | 100%
1899-12-31 | 100%
1899-12-31 | 100%

## Cost Contingency
Cost/Contingency
Project Costs (MUSD) |  |  | Contingency (MUSD)
Base Case | Forecast | Cost Overun | Base Case | Utilized | Forecast | Potential Savings
769.3 | 971.8 | 202.5 | 28.6 | 31.5 | 0 | 0

## Source Of Founding
Head | Value | Sponsor Share | Partners Share
Contingency | 27.1
Standby Equity | 33.1
Standby Debt | 0
Additional Loans | 0
Additional EBL | 0
Additional EGR | 0
Withheld EPC Milestone Payment | 0
LDs | 47.1
WCF | 20.8
Shareholder injection | 0
Unresolved | 0