## Projects
Project ID (TP) | PRJ-100
Project name | Falcon Solar PV
Location | Southern Corridor
GEO | Region A
Cluster
Country | Region A
Technology | Wind
Capacity | 339 MW
Contract Price | USD 217 million
Contract Type | Split EPC
Offtaker | Regional Power Purchaser
Contractor | Meridian Builders
OEM | SunCell, InvertaTech
O&M | In-house O&M
EPC
Contractual Key Dates
Key Milestones | PPA | Capacity | EPC Contract | Forecast |  | Delays
|  |  |  | EPC | PC
LNTP | 2023-10-06 |  | 2023-10-06 |  | 2023-10-06 | -2
NTP | 2024-07-11 |  | 2024-07-11 |  | 2024-07-11 | 3
FC |  |  |  |  | 2025-03-18 | -1
ECD |  |  | 2025-12-10 |  | 2025-12-10 | 0
ICOD1 |  | 110 MW | 2026-01-25 |  | 2026-03-26 | -1
ICOD2 |  | 110 MW | 2026-02-24 |  | 2026-03-26 | -2
PCOD | 2027-07-05 |  | 2026-03-13 |  | 2026-04-12 | 2
COD3 |  | 119.3 MW
`
[7 empty] | No | Key Milestone (Monthly) | Baseline Date | Forecast Date | Actual Date

## Key Concerns Mitigations,QA QC
Key Concerns and Mitigations
Key Concerns | Mitigations | Severity | Impact
Shortage of skilled electricians during peak installation period. | Claim is being reviewed against contract entitlements. | Low | Contractual
Grid connection studies pending approval from the transmission operator; risk to energisation date. | Weekly coordination meetings held with the grid operator; phased approvals proposed. | Low | Schedule
Design change requested by the offtaker for the substation layout. | Change order under evaluation; interim design frozen for non-affected areas. | Low | Schedule
Subcontractor mobilisation behind plan for civil works. | Change order under evaluation; interim design frozen for non-affected areas. | High | Schedule
QA/QC | Values
FAT (Reported/Done/Expected Total) | 67/55/90
NCR (Open / Total) | 39/102
Critical NCRs | 0
RFI Offshore (Approved/Inspected) | 80/95
RFI Onshore (Approved/Inspected) | 2053/2232

## Cost Contingency
Cost/Contingency
Project Costs (MUSD) |  |  | Contingency (MUSD)
Base Case | Forecast | Cost Overun | Base Case | Utilized | Forecast | Potential Savings
208.6 | 193.4 | -15.2 | 3.1 |  |  | 3.3

## Project Progress
Project Progress |  |  |  |  | Payment Milestones Progress |  |  |  | Key Achievements
Category | Weight | Early | Late | Actual | Category | Weight | Plan | Actual
Engineering | 10% | 100% | 100% | 99.58% | Overall |  | 83.28% | 70.42% | Inverter station pre-commissioning started.
Procurement | 35% | 100% | 91.62% | 97.58% |  |  |  |  | BESS containers delivered to site.
Construction | 45% | 67.88% | 45.22% | 36.42% |  |  |  |  | Transmission line stringing 80% complete.
Commissioning | 10% | 27.09% | 1.732% | 2.141%
OVERALL | 100% | 79.06% | 64.54% | 63.19%

## Contractor Claims
Contractor Claims
Total Cost Claim | Total Extension of Time Claim | Remarks
821249.64 | 35 | Under review

## Critical Path Analysis
Critical Path Analysis | Float(d)
Turbine Foundations > Erection > Energisation | 14 days
Module Delivery > Installation > Mechanical Completion > Commissioning | 28 days
Intake Works > Membrane Installation > Performance Test | 21 days
Transformer Delivery > Installation > Testing > Energisation | 7 days
Transformer Delivery > Installation > Testing > Energisation | 0 days
Transformer Delivery > Installation > Testing > Energisation | 0 days

## Project Key Milestones
Project Key Milestones
Sr. No. | Key Milestone (Monthly) | Baseline Date | Forecast Date | Actual Date
| EPC contract signed | Baseline | Forecast | Actual
1 | Limited notice to proceed | 2024-09-03 |  | 2024-08-20
2 | Full notice to proceed | 2024-09-28 |  | 2024-08-30
3 | Financial close | 2024-11-24 |  | 2025-01-08
4 | Detailed design 50% complete | 2024-12-06 |  | 2025-02-12
5 | Main equipment orders placed | 2025-01-24 |  | 2025-03-18
6 | Site mobilisation | 2025-01-21 |  | 2025-03-19
7 | Piling works start | 2025-02-18 |  | 2025-03-19
8 | Foundations complete | 2024-11-13 |  | 2025-04-26
9 | Main equipment delivered | 2025-05-23 |  | 2025-05-01
10 | Substation energisation | 2025-06-28 |  | 2025-05-01
11 | Block 1 mechanical completion | 2025-01-17 |  | 2025-05-29
12 | Block 2 mechanical completion | 2025-04-22 |  | 2025-06-07
13 | Backfeed power available | 2025-02-04 |  | 2025-06-26
14 | First power / synchronisation | 2025-02-25 | 2025-08-03
15 | Block 1 commissioning | 2025-02-08 | 2025-08-31
16 | Block 2 commissioning | 2025-06-28 | 2025-09-04
17 | Reliability run | 2025-04-17 | 2025-09-19
18 | Performance test | 2025-07-12 | 2025-09-27
19 | Partial commercial operation | 2025-08-20 | 2025-11-08
20 | Commercial operation date | 2025-09-27 | 2025-11-11
21 | Punch-list closure | 2025-09-30 | 2025-11-11
22 | Final acceptance | 2025-09-30 | 2025-11-11
23 | EPC contract signed | 2025-09-30 | 2025-11-11
24 | Limited notice to proceed | 2025-11-13 | 2025-11-13
25 | Full notice to proceed | 2025-11-17 | 2025-11-17
26 | Financial close | 2025-05-15 | 2025-11-22
27 | Detailed design 50% complete | 2025-11-30 | 2025-11-30
28 | Main equipment orders placed | 2025-11-08 | 2025-12-02
29 | Site mobilisation | 2025-09-23 | 2025-12-03
30 | Piling works start | 2025-12-09 | 2025-12-07
31 | Foundations complete | 2025-12-10 | 2025-12-10
32 | Main equipment delivered | 2025-12-10 | 2025-12-10
33 | Substation energisation | 2025-12-10 | 2025-12-10
34 | Block 1 mechanical completion | 2025-12-05 | 2025-12-20
35 | Block 2 mechanical completion | 2025-12-29 | 2026-01-01
36 | Backfeed power available | 2026-01-02 | 2026-01-07
37 | First power / synchronisation | 2025-12-09 | 2026-01-09
38 | Block 1 commissioning | 2025-11-22 | 2026-01-13
39 | Block 2 commissioning | 2025-11-29 | 2026-01-13
40 | Reliability run | 2026-01-16 | 2026-01-21
41 | Performance test | 2026-01-16 | 2026-01-21
42 | Partial commercial operation | 2026-01-16 | 2026-01-21
43 | Commercial operation date | 2026-01-25 | 2026-01-27
44 | Punch-list closure | 2026-01-30 | 2026-02-04
45 | Final acceptance | 2026-01-17 | 2026-02-11
46 | EPC contract signed | 2026-02-14 | 2026-02-14
47 | Limited notice to proceed | 2026-02-04 | 2026-02-17
48 | Full notice to proceed | 2026-02-24 | 2026-02-24
49 | Financial close | 2026-02-24 | 2026-02-24
50 | Detailed design 50% complete | 2026-03-12 | 2026-03-12
51 | Main equipment orders placed | 2026-03-13 | 2026-03-13

## S-Curve
Date | No. | Project Baseline Early T0 |  | Project Baseline Late T0 |  | Actual |  | Forecast
|  | Monthly Progress (%) | Ac, Progress (%) | Monthly Progress (%) | Ac, Progress (%) | Monthly Progress (%) | Ac, Progress (%) | Monthly Progress (%) | Ac, Progress (%)

## Payment Milestones S-curve
Date | Plan Cum % | Actual Cum % | Forecast Cum %

## Source Of Founding
Head | Value | Sponsor Share | Partners Share