## Projects
Project ID (TP | PRJ-103
Project name | Horizon Solar PV
Location | Eastern Basin
GEO | Region B
Cluster
Country | Region B
Technology | PV
Capacity | 1441 MW
Contract Price
Contract Type | IPP / EPC LSTK
Offtaker | Regional Power Purchaser
Contractor | Summit Construction Co.
OEM | PanelWorks, PowerStack
O&M | In-house O&M
EPC
Contractual Key Dates | [5 empty] | 🟢
Key Milestones | PPA | Capacity | EPC Contract | Forecast |  | Delays
|  |  |  | EPC | PC
LNTP | 2023-08-19 | - |  | 2023-09-23 | 2023-09-23
NTP | 2023-11-18 | - |  | 2023-11-19 | 2023-11-19
FC | 2023-12-07 | - |  | 2024-03-12 | 2024-03-12
ECD | 2025-02-18 | - |  | 2025-08-04 | 2025-08-04 | 2
COD1 | 2025-06-18 | 1,0 MW |  | 2025-10-18 | 2025-10-18 | 3
COD2 | 2025-10-18 | 1,0 MW |  | 2025-10-18 | 2025-10-18 | -1
PCOD | 2026-08-18 | 1,0 MW |  | 2026-08-18 | 2026-08-18 | 0
[7 empty] | No | Key Milestone (Monthly) | Baseline Date | Forecast Date | Actual Date

## Key Concerns Mitigations,QA QC
Key Concerns and Mitigations
Key Concerns | Mitigations | Severity | Impact
Shortage of skilled electricians during peak installation period. | Recovery schedule requested from the contractor and tracked weekly. | Medium | HSE
Customs clearance delays for imported modules. | Additional crews mobilised from sister projects. | Low | Schedule
Currently there are no key concerns to highlight. | Recovery schedule requested from the contractor and tracked weekly. |  | Contractual
Design change requested by the offtaker for the substation layout. | Claim is being reviewed against contract entitlements. |  | QA/QC
Customs clearance delays for imported modules. | Weekly coordination meetings held with the grid operator; phased approvals proposed. |  | Finance
Subcontractor mobilisation behind plan for civil works. | Additional crews mobilised from sister projects. | High | Contractual
QA/QC | Values
FAT (Actual / Total) | 160/213
NCR (Open / Total) | 6/10
Critical NCRs
FON (Open / Total) | 224/367
TOP (Actual / Total) | 43/72

## Cost Contingency
Cost/Contingency
Project Costs (MUSD) |  |  | Contingency (MUSD)
Base Case | Forecast | Cost Overun | Base Case | Utilized | Forecast | Potential Savings
1758.7 | 1765.7 | 7 | 13.8 | 0 | 13.8 | 0

## Project Progress
Project Progress |  |  |  |  | Payment Milestones Progress |  |  |  |  | Key Achievements
Category | Weight | Early | Late | Actual | Category | Weight | Plan | Actual
Engineering | 10% | 100% | 99.88% | 98.69% | Engineering | 8.5% |  | 99.88% | 99.9% | Seawater intake structure completed.
Preliminary and Permitting | 1% | 100% | 99.05% | 96.91% | Procurement | 37.8% |  | 100% | 100% | Control building handed over to O&M team.
Procurement | 5% | 100% | 100% | 100% | Construction | 47% | 99.76% | 1 | 98.2% | Control building handed over to O&M team.
Manufacturing & Delivery | 30% | 100% | 100% | 100% | Commissioning | 6.7% | 27.02% | 9.469% | 13.8% | Inverter station pre-commissioning started.
Construction | 44% | 99.64% | 95.02% | 99.52% | OVERALL | 100% | 94.55% | 92.2% | 93.4% | Main substation energised successfully.
Commissioning | 10% | 72.81% | 52.83% | 45.6% | [5 empty] | Foundation works for all turbines completed.
OVERALL | 100% | 97.03% | 92.9% | 93.84%
`

## Contractor Claims
Contractor Claims
Total Cost Claim | Total Extension of Time Claim | Remarks
41 M USD | 9 months

## Critical Path Analysis
Critical Path Analysis | Float(d)
Intake Works > Membrane Installation > Performance Test | 28 days
Grid Studies > Substation Energisation > Backfeed > COD | 7 days
Intake Works > Membrane Installation > Performance Test | 21 days

## Project Key Milestones
Project Key Milestones
Sr. No. | Key Milestone (Monthly) | Baseline Date | Forecast Date | Actual Date
1 | EPC contract signed | 2024-05-09 |  | 2024-06-25
2 | Limited notice to proceed | 2024-05-25 |  | 2024-08-05
3 | Full notice to proceed | 2024-06-30 |  | 2024-06-04
4 | Financial close | 2024-08-13 |  | 2024-08-10
5 | Detailed design 50% complete | 2024-09-01 |  | 2024-09-12
6 | Main equipment orders placed | 2024-10-10 |  | 2024-11-09
7 | Site mobilisation | 2024-10-31 |  | 2024-12-17
8 | Piling works start | 2024-10-18 |  | 2025-02-16
9 | Foundations complete | 2024-09-28 |  | 2024-11-20
10 | Main equipment delivered | 2024-12-12 |  | 2025-01-05
11 | Substation energisation | 2024-12-24 |  | 2024-09-24
12 | Block 1 mechanical completion | 2024-12-19 |  | 2025-03-20
13 | Block 2 mechanical completion | 2025-02-15 |  | 2025-02-02
14 | Backfeed power available | 2025-03-14 |  | 2025-04-10
15 | First power / synchronisation | 2025-02-18 | 2025-08-04
16 | Block 1 commissioning | 2025-03-16 | 2025-08-30
17 | Block 2 commissioning | 2025-03-22 | 2025-09-05 | 2025-06-07
18 | Reliability run | 2025-04-08 | 2025-09-06
19 | Performance test | 2025-06-03 | 2025-10-02
20 | Partial commercial operation | 2025-06-18 | 2025-10-18
1 | Commercial operation date | 2024-05-21 |  | 2024-06-06
2 | Punch-list closure | 2024-06-19 |  | 2024-06-25
3 | Final acceptance | 2024-07-19 |  | 2024-07-05
4 | EPC contract signed | 2024-09-16 |  | 2024-11-26
5 | Limited notice to proceed | 2024-09-21 |  | 2024-10-07
6 | Full notice to proceed | 2024-10-01 |  | 2024-12-05
7 | Financial close | 2024-11-18 |  | 2024-11-07
8 | Detailed design 50% complete | 2025-01-10 |  | 2025-03-06
9 | Main equipment orders placed | 2024-12-01 |  | 2025-01-10
10 | Site mobilisation | 2024-11-21 |  | 2024-10-28
11 | Piling works start | 2025-01-10 |  | 2025-03-10
12 | Foundations complete | 2025-02-18 |  | 2025-03-10
13 | Main equipment delivered | 2025-02-14 |  | 2025-02-07
14 | Substation energisation | 2025-03-07 | 2025-08-02
15 | Block 1 mechanical completion | 2025-04-18 | 2025-09-19
16 | Block 2 mechanical completion | 2025-04-21 |  | 2025-03-12
17 | Backfeed power available | 2025-07-09 |  | 2025-07-08
18 | First power / synchronisation | 2025-05-22 | 2025-09-20
19 | Block 1 commissioning | 2025-07-10 | 2025-09-18
20 | Block 2 commissioning | 2025-08-03 | 2025-09-06
21 | Reliability run | 2025-07-11 | 2025-09-20
22 | Performance test | 2025-10-03 | 2025-10-03
23 | Partial commercial operation | 2025-10-18 | 2025-10-18

## S-Curve
Date | No. | Project Baseline Early T0 |  | Project Baseline Late T0 |  | Actual |  | Forecast
|  | Monthly Progress (%) | Ac, Progress (%) | Monthly Progress (%) | Ac, Progress (%) | Monthly Progress (%) | Ac, Progress (%) | Monthly Progress (%) | Ac, Progress (%)
2023-08-19 |  | 0% | 0% | 0% | 0% | 0% | 0%
2023-09-19 |  | 0.2313% | 0.2313% | 0% | 0% | 0.5432% | 0.5432%
2023-10-19 |  | 0.9847% | 1.216% | 0.06871% | 0.06871% | 1.899% | 2.442%
2023-11-19 |  | 1.24% | 2.456% | 0.6223% | 0.691% | 1.479% | 3.922%
2023-12-20 |  | 2.156% | 4.612% | 0.8185% | 1.509% | 1.338% | 5.259%
2024-01-19 |  | 2.329% | 6.941% | 1.131% | 2.641% | 2.268% | 7.527%
2024-02-19 |  | 3.152% | 10.09% | 1.949% | 4.59% | 2.896% | 10.42%
2024-03-20 |  | 3.606% | 13.7% | 2.087% | 6.677% | 4.285% | 14.71%
2024-04-20 |  | 5.179% | 18.88% | 2.792% | 9.469% | 4.168% | 18.88%
2024-05-21 |  | 6.324% | 25.2% | 3.213% | 12.68% | 8.409% | 27.29%
2024-06-19 |  | 7.226% | 32.43% | 4.207% | 16.89% | 9.428% | 36.71%
2024-07-20 |  | 7.813% | 40.24% | 5.184% | 22.07% | 4.742% | 41.46%
2024-08-19 |  | 9.935% | 50.17% | 7.159% | 29.23% | 9.006% | 50.46%
2024-09-19 |  | 9.296% | 59.47% | 7.747% | 36.98% | 9.063% | 59.53%
2024-10-19 |  | 10.21% | 69.68% | 9.941% | 46.92% | 10.31% | 69.84%
2024-11-19 |  | 8.803% | 78.48% | 9.78% | 56.7% | 8.039% | 77.88%
2024-12-20 |  | 7.521% | 86% | 9.434% | 66.13% | 2.672% | 80.55%
2025-01-19 |  | 5.734% | 91.74% | 9.199% | 75.33% | 4.48% | 85.03%
2025-02-19 |  | 3.568% | 95.3% | 9.29% | 84.62% | 5.759% | 90.79%
2025-03-21 |  | 2.011% | 97.32% | 7.808% | 92.43% | 0.01976 | 0.92763
2025-04-21 |  | 1.78% | 99.1% | 3.939% | 96.37% | 0.017865 | 0.94549
2025-05-22 |  | 0.7968% | 99.89% | 3.06% | 99.43% | 0.0059587 | 0.95145
2025-06-19 |  | 0.1071% | 100% | 0.3925% | 99.82% | 0.0062453 | 0.9577
2025-07-20 |  | 0% | 100% | 0.0476% | 99.87%
2025-08-19 |  | 0% | 100% | 0.0476% | 99.92%
2025-09-19 |  | 0% | 100% | 0.07141% | 99.99%
2025-10-19 |  | 0% | 100% | 0.0119% | 100%
2025-11-19 |  | 0% | 100% | 0% | 100%
2025-12-20 |  | 0% | 100% | 0% | 100%
2026-01-19 |  | 0% | 100% | 0% | 100%
2026-02-19 |  | 0% | 100% | 0% | 100%
2026-03-21 |  | 0% | 100% | 0% | 100%
2026-04-21 |  | 0% | 100% | 0% | 100%
2026-05-22 |  | 0% | 100% | 0% | 100%
2026-06-19 |  | 0% | 100% | 0% | 100%
2026-07-20 |  | 0% | 100% | 0% | 100%
2026-08-19 |  | 0% | 100% | 0% | 100%
2026-09-19
2026-10-19
2026-11-19
2026-12-20
2027-01-19
2027-02-19
2027-03-21

## Payment Milestones S-curve
Date | Plan Cum % | Actual Cum % | Forecast Cum %
2023-10-18 | 0.8108% | 0.5072%
2023-11-18 | 1.024% | 0.5072%
2023-12-18 | 2.156% | 2.136%
2023-12-19 | 2.156% | 2.136%
2024-01-18 | 6.301% | 6.308%
2024-02-18 | 8.835% | 8.835%
2024-03-19 | 10.51% | 10.51%
2024-04-19 | 12.24% | 12.28%
2024-05-19 | 16.42% | 12.28%
2024-06-18 | 21.12% | 20.2%
2024-07-18 | 26.6% | 26.21%
2024-08-18 | 33.18% | 30.28%
2024-09-17 | 39.99% | 37.17%
2024-10-18 | 45.97% | 41.8%
2024-11-18 | 52.08% | 48.49%
2024-12-19 | 58.31% | 0.56914
2025-01-18 | 65.71% | 0.5754
2025-02-18 | 73.24% | 0.68781
2025-03-20 | 79.81% | 0.75333
2025-04-20 | 86.46% | 0.82879
2025-05-21 | 92.07% | 0.87725
2025-06-18 | 94.31% | 0.89859
2025-07-19 | 94.6% | 0.92171 | 92.17%
2025-08-18 | 94.88%
2025-09-17 | 95.16%
2025-10-18 | 95.45%
2025-11-18 | 96.36%
2025-12-19 | 97.27%
2026-01-18 | 97.72%
2026-02-18 | 98.18%
2026-03-20 | 98.63%
2026-04-20 | 99.08%
2026-05-21 | 99.31%
2026-06-18 | 99.55%
2026-07-19 | 99.77%
2026-08-18 | 100%
2026-09-18 | 100%

## Source Of Founding
Head | Value | Sponsor Share | Partners Share
Contingency
Standby Equity
Standby Debt
Additional Loans
Additional EBL
Additional EGR
Withheld EPC Milestone Payment
LDs
WCF
Shareholder injection
Unresolved