## Projects
Project ID (TP) | PRJ-116
Project name | Topaz CSP Plant
Location | Gulf Coast Site
GEO | Region C
Cluster | Cluster B
Country | Region C
Technology | CSP
Capacity | 111 MW
Contract Price | BOO 21 years
Contract Type | Split EPC
Offtaker | State Water Authority
Contractor | Crescent Infra & Power
OEM | SunCell, InvertaTech
O&M
EPC
Contractual Key Dates
Key Milestones | PPA | Capacity | EPC Contract | Forecast |  | Delays
|  |  |  | EPC | PC
LNTP | 2021-03-20 | - | 2021-03-20 |  | 2021-03-20 | 0
NTP | 2021-06-17 | - | 2021-06-17 |  | 2021-06-17 | 1
COD | - | 111 MW | 2025-06-16 |  | 30-Apr-25 | 3
IA | 2024-03-22 | 111 MW | 2025-07-17 |  | 2025-07-17 | 0
[7 empty] | No | Key Milestone (Monthly) | Baseline Date | Forecast Date | Actual Date

## Key Concerns Mitigations,QA QC
Key Concerns and Mitigations
Key Concerns | Mitigations | Severity | Impact
Pending permit for temporary access road. | Claim is being reviewed against contract entitlements. | High | HSE
Grid connection studies pending approval from the transmission operator; risk to energisation date. | Change order under evaluation; interim design frozen for non-affected areas. | Low | Cost
Design change requested by the offtaker for the substation layout. | Claim is being reviewed against contract entitlements. | High | Schedule
Customs clearance delays for imported modules. | Recovery schedule requested from the contractor and tracked weekly. | Low | Schedule
Extreme summer temperatures limiting working hours on site. | Weekly coordination meetings held with the grid operator; phased approvals proposed. | Medium | Cost
Currently there are no key concerns to highlight. | Night shifts introduced for critical activities. | Low | Finance
QA/QC | Values
FAT (Actual / Total) | 78/162
NCR (Open / Total) | 105/215
Critical NCRs | 0
SOR (Site Observation Report) | 3
TOP (Actual / Total) | 89/222

## Cost Contingency
Cost/Contingency
Project Costs (MUSD) |  |  | Contingency (MUSD)
Base Case | Forecast | Cost Overun | Base Case | Utilized | Forecast | Potential Savings
853.7 | 921 | 67.3 | 29.7 | 30.6 | - | -

## Project Progress
Project Progress |  |  |  |  | Payment Milestones Progress |  |  |  | Key Achievements
Category | Weight | Early | Late | Actual | Category | Weight | Plan | Actual
Engineering | 10% | 100% | 100% | 100% | Package A | 65.3% | 69.91% | 68.56% | Foundation works for all turbines completed.
Procurement | 40% | 100% | 100% | 99.87% | Package B | 34.7% | 41.11% | 38.81% | Seawater intake structure completed.
Construction | 40% | 100% | 100% | 99.69% | OVERALL | 100% | 100% | 96.8% | Tracker installation completed for Phase 1.
Commissioning | 10% | 100% | 100% | 95.56%
OVERALL | 100% | 100% | 100% | 99.39%

## Contractor Claims
Contractor Claims
Total Cost Claim | Total Extension of Time Claim | Remarks
25 M USD | 2 months | Under review

## Critical Path Analysis
Critical Path Analysis | Float(d)
Transformer Delivery > Installation > Testing > Energisation | 35 days
Turbine Foundations > Erection > Energisation | 0 days

## Project Key Milestones
Project Key Milestones
Sr. No. | Key Milestone (Monthly) | Baseline Date | Forecast Date | Actual Date
1 | EPC contract signed | 2023-09-16 | 2024-05-15 | 2024-05-17
2 | Limited notice to proceed | 2024-01-10 | 2024-04-20 | 2024-04-23
3 | Full notice to proceed | 2024-01-05 | 2024-06-01 | 2024-04-25
4 | Financial close | 2024-01-11 | 2024-08-30 | 2024-09-05
5 | Detailed design 50% complete | 2023-08-12 | 2024-06-11 | 2024-06-01
6 | Main equipment orders placed | 2023-10-05 | 2024-06-16 | 2024-06-16
7 | Site mobilisation | 2024-01-11 | 2024-07-07 | 2024-05-09
8 | Piling works start | 2023-09-19 | 2024-07-13 | 2024-07-09
9 | Foundations complete | 2023-08-17 | 2024-07-16 | 2024-07-16
10 | Main equipment delivered | 2023-10-22 | 2024-07-17 | 2024-07-17
11 | Substation energisation | 2024-03-07 | 2024-08-25 | 2024-08-11
12 | Block 1 mechanical completion | 2024-01-19 | 2024-10-03 | 2024-10-19
13 | Block 2 mechanical completion | 2023-10-15 | 2024-08-01 | 2024-08-16
14 | Backfeed power available | 2023-11-09 | 2024-08-16 | 2024-08-16
15 | First power / synchronisation | 2024-04-14 | 2024-10-05 | 2024-10-26
16 | Block 1 commissioning | 2023-10-26 | 2024-08-20 | 2024-09-16
17 | Block 2 commissioning | 2023-11-27 | 2024-09-16 | 2024-09-16
18 | Reliability run | 2023-05-07 | 2025-06-01
19 | Performance test | 2024-10-06 | 2024-10-26 | 2024-10-31
20 | Partial commercial operation | 2024-10-17 | 2025-06-16
21 | Commercial operation date | 2024-06-10 | 2025-06-19
22 | Punch-list closure | 2024-03-24 | 2025-06-19
23 | Final acceptance | 2024-06-13 | 2025-06-25

## S-Curve
Date | No. |  | Project Baseline Early T0 |  |  | Project Baseline Late T0 |  |  | Actual |  |  | Forecast
|  |  | Monthly Progress (%) | Ac, Progress (%) |  | Monthly Progress (%) | Ac, Progress (%) |  | Monthly Progress (%) | Ac, Progress (%) |  | Monthly Progress (%) | Ac, Progress (%)
2021-05-18 | -1 | 0.005885 | 0.5885% | 0.2212% | 0.1287% | 0.1287% | 0.0362% | 0.4911% | 0.4911% | 0.1783%
2021-06-17 | 1 | 0.0073321 | 1.322% | 0.8007% | 0.2274% | 0.3561% | 0.1578% | 1.083% | 1.574% | 0.8918%
2021-07-18 | 2 | 0.023265 | 3.648% | 2.742% | 0.6294% | 0.9855% | 0.5664% | 1.223% | 2.797% | 2.306%
2021-08-17 | 3 | 0.01515 | 5.163% | 5.677% | 0.8199% | 1.805% | 1.406% | 0.2291% | 3.026% | 3.86%
2021-09-17 | 4 | 0.011786 | 6.342% | 9.426% | 1.785% | 3.59% | 3.311% | 2.931% | 5.957% | 7.34%
2021-10-18 | 5 | 0.0027954 | 6.621% | 13.37% | 0.6655% | 4.256% | 5.643% | -0.1875% | 5.77% | 10.69%
2021-11-17 | 6 | 0.0040929 | 7.031% | 17.61% | 0.6459% | 4.902% | 8.402% | 0.1544% | 5.924% | 14.15%
2021-12-18 | 7 | 0.012176 | 8.248% | 22.74% | 1.149% | 6.051% | 11.95% | -0.3285% | 5.595% | 17.38%
2022-01-17 | 8 | 0.0061372 | 8.862% | 28.32% | -0.1332% | 5.918% | 15.4% | 1.231% | 6.827% | 21.47%
2022-02-17 | 9 | -0.00039579 | 8.822% | 33.88% | 0.6594% | 6.577% | 19.32% | 0.261% | 7.088% | 25.75%
2022-03-20 | 10 | -0.01209 | 7.613% | 38.54% | -0.5091% | 6.068% | 22.87% | -0.1813% | 6.906% | 29.9%
2022-04-17 | 11 | 0.0094519 | 8.559% | 43.9% | 1.046% | 7.115% | 27.17% | -2.138% | 4.768% | 32.57%
2022-05-18 | 12 | -0.0045038 | 8.108% | 48.92% | -0.3889% | 6.726% | 31.19% | 1.361% | 6.129% | 36.17%
2022-06-17 | 13 | 0.0014225 | 8.25% | 54.05% | 0.501% | 7.227% | 35.57% | -0.2296% | 5.899% | 39.61%
2022-07-18 | 14 | -0.0059167 | 7.659% | 58.74% | 0.2857% | 7.512% | 40.16% | -1.494% | 4.406% | 42.04%
2022-08-17 | 15 | 0.0025807 | 7.917% | 63.62% | -1.039% | 6.473% | 44% | 1.994% | 6.4% | 45.83%
2022-09-17 | 16 | -0.0076239 | 7.154% | 67.95% | 0.5327% | 7.006% | 48.22% | -1.377% | 5.022% | 48.67%
2022-10-18 | 17 | -0.0019625 | 6.958% | 72.14% | 0.5976% | 7.604% | 52.88% | -3.7% | 1.322% | 49.25%
2022-11-17 | 18 | 0.015231 | 8.481% | 77.44% | 0.9461% | 8.55% | 58.23% | 2.931% | 4.253% | 51.58%
2022-12-18 | 19 | 0.00034537 | 8.516% | 82.76% | 0.306% | 8.856% | 63.81% | 1.517% | 5.77% | 54.93%
2023-01-17 | 20 | 0.0036004 | 8.876% | 88.36% | 0.4747% | 9.33% | 69.74% | 0.9267% | 6.696% | 58.93%
2023-02-17 | 21 | -0.023913 | 6.485% | 92.21% | 0.3652% | 9.696% | 75.96% | -2.566% | 4.13% | 61.18%
2023-03-20 | 22 | -0.011045 | 5.38% | 95.29% | -0.1729% | 9.523% | 82.04% | 2.776% | 6.906% | 65.33%
2023-04-17 | 23 | -0.01395 | 3.985% | 97.45% | -0.4561% | 9.067% | 87.78% | -6.343% | 0.5634% | 65.54%
2023-05-18 | 24 | -0.013774 | 2.608% | 98.75% | -2.756% | 6.311% | 91.51% | 6.663% | 7.227% | 69.92%
2023-06-17 | 25 | -0.014284 | 1.179% | 99.25% | -2.122% | 4.189% | 93.8% | -3.423% | 3.804% | 71.96%
2023-07-18 | 26 | -0.0070646 | 0.4728% | 99.42% | -0.7886% | 3.4% | 95.58% | 2.709% | 6.513% | 75.83%
2023-08-17 | 27 | 0.0021628 | 0.6891% | 99.69% | -0.2271% | 3.173% | 97.23% | 0.3796% | 6.892% | 79.97%
2023-09-17 | 28 | -0.0034835 | 0.3407% | 99.81% | -1.395% | 1.778% | 98.05% | -1.885% | 5.007% | 82.8%
2023-10-18 | 29 | -0.00047664 | 0.2931% | 99.9% | -0.2094% | 1.568% | 98.76% | -2.202% | 2.806% | 84.22%
2023-11-17 | 30 | 8.1679e-07 | 0.2932% | 100% | 0.9327% | 2.501% | 100% | -0.9107% | 1.895% | 85.11%
2023-12-18 | 31 | -0.0029315 | 0% | 100% | -2.501% | 0% | 100% | 0.6426% | 2.538% | 86.37%
2024-01-17 | 32 | 0 | 0% | 100% | 0% | 0% | 100% | 1.883% | 4.421% | 88.81%
2024-02-17 | 33 | 0 | 0% | 100% | 0% | 0% | 100% | -2.261% | 2.16% | 89.85%
2024-03-19 | 34 | 0 | 0% | 100% | 0% | 0% | 100% | 0.6955% | 2.855% | 91.3%
2024-04-17 | 35 | 0 | 0% | 100% | 0% | 0% | 100% | -1.476% | 1.38% | 91.91%
2024-05-18 | 36 | 0 | 0% | 100% | 0% | 0% | 100% | 1.073% | 2.453% | 93.12%
2024-06-17 | 37 | 0 | 0% | 100% | 0% | 0% | 100% | -1.823% | 0.6303% | 93.36%
2024-07-18 | 38 | 0 | 0% | 100% | 0% | 0% | 100% | 2.34% | 2.971% | 94.88%
2024-08-17 | 39 | 0 | 0% | 100% | 0% | 0% | 100% | -1.04% | 1.931% | 95.79%
2024-09-17 | 40 | 0 | 0% | 100% | 0% | 0% | 100% | -0.5509% | 1.38% | 96.4%
2024-10-18 | 41 | 0 | 0% | 100% | 0% | 0% | 100% | 0.4254% | 1.805% | 97.24%
2024-11-17 | 42 | 0 | 0% | 100% | 0% | 0% | 100% | -1.219% | 0.5859% | 97.46%
2024-12-18 | 43 | 0 | 0% | 100% | 0% | 0% | 100% | 0.6597% | 1.246% | 98%
2025-01-17 | 44 | 0 | 0% | 100% | 0% | 0% | 100% | -0.7972% | 0.4484% | 98.16%
2025-02-17 | 45 | 0 | 0% | 100% | 0% | 0% | 100% | 1.248% | 1.696% | 98.94%
2025-03-20 | 46 | 0 | 0% | 100% | 0% | 0% | 100% | -1.088% | 0.6082% | 99.17%
2025-04-17 | 47 | 0 | 0% | 100% | 0% | 0% | 100% | -0.306% | 0.3021% | 99.27% | 0% | 1.089% | 99.73%
2025-05-18 | 48 | 0 | 0% | 100% | 0% | 0% | 100% |  |  |  | -0.7613% | 0.3273% | 99.84%
2025-06-17 | 49 | 0 | 0% | 100% | 0% | 0% | 100% |  |  |  | 0.1211% | 0.4484% | 100%

## Payment Milestones S-curve
Date | Plan Cum % | Actual Cum % | Forecast Cum %
2025-02-17 | 8.718% | 3.163%
2025-02-18 | 9.154% | 8.172%
2025-02-19 | 13.21% | 8.58%
2025-02-20 | 15.94% | 11.1%
2025-02-21 | 19.89% | 13.6%
2025-02-22 | 24.1% | 13.6%
2025-02-23 | 28.67% | 16.1%
2025-02-24 | 32.82% | 16.66%
2025-02-25 | 37.21% | 17.59%
2025-02-26 | 40.44% | 23.65%
2025-02-27 | 43.89% | 28.94%
2025-02-28 | 48.31% | 31.92%
2025-03-01 | 52.12% | 35.09%
2025-03-02 | 56.12% | 38.66%
2025-03-03 | 59.77% | 40.76%
2025-03-04 | 64.81% | 42.61%
2025-03-05 | 68.85% | 44.38%
2025-03-06 | 73.02% | 50.6%
2025-03-07 | 76.62% | 52.64%
2025-03-08 | 80.07% | 60.86%
2025-03-09 | 82.55% | 67.57%
2025-03-10 | 85.04% | 67.57%
2025-03-11 | 87.4% | 71.56%
2025-03-12 | 89.39% | 77.18%
2025-03-13 | 91.25% | 80.33%
2025-03-14 | 93.13% | 82.78%
2025-03-15 | 94.99% | 83.76%
2025-03-16 | 96.85% | 85.9%
2025-03-17 | 98.36% | 88.4%
2025-03-18 | 99.84% | 90.84%
2025-03-19 | 100% | 91.61%
2025-03-20 | 100% | 92.76%
2025-03-21 | 100% | 94.66%
2025-03-22 | 100% | 95.34%
2025-03-23 | 100% | 96.12%
2025-03-24 | 100% | 96.5%
2025-03-25 | 100% | 96.5%
2025-03-26 | 100% | 96.66%
2025-03-27 | 100% | 96.66%
2025-03-28 | 100% | 96.69%
2025-03-29 | 100% | 96.69%
2025-03-30 | 100% | 96.71%
2025-03-31 |  | 96.71%
2025-04-01 |  | 96.71%
2025-04-02 |  | 96.71%
2025-04-03 |  | 96.71%
2025-04-04 |  | 96.71%

## Source Of Founding
Head | Value | Sponsor Share | Partners Share
Contingency | 0 | 0 | 0
Standby Equity | 4.4 | 1.5 | 3.1
Standby Debt | 8 | 35 | 0
Additional Loans | 22.7 | 19.7 | 0
Additional EBL | 3.5 | 0 | 0
Additional EGR | 29.6 | 19.6 | 0
Withheld EPC Milestone Payment | 0 | 0 | 33.3
LDs | 42.6 | 20.3 | 0
WCF | 0 | 0 | 0
Shareholder injection | 0 | 6.5 | 0
Unresolved | 28.5 | 0 | 0